## Estimating Model
Modules/Features/Functions | Complexity | Frontend Build | Backend Build | System Test | UAT | Estimated Total | FTE | Weeks | Months
TOTALS |  | 2344 | 2936 | 1063 | 544 | 7647
Business Design |  | 0 |  |  |  | 260 | 2 | 3.25 | 0.8125 | 2024-05-22 | 2024-06-15 09:00
Process Design |  | 0 | 0 | 0 | 0
Order flow (Receipt / Delivery) | low | 0 | 0 | 0 | 0 | 24
Order Structure | low | 0 | 0 | 0 | 0 | 24
Integration mapping | low |  |  |  |  | 32
Process Flow | low |  |  |  |  | 24
SaaS Offering strategy |  | 0 | 0 | 0 | 0
Market research and analysis | low |  |  |  |  | 40
JMI Feature Bridge to SaaS analysis | low |  |  |  |  | 20
Onboarding strategy | low |  |  |  |  | 40
Product and Form Design |  | 0 | 0 | 0 | 0
Product offerings | low | 0 | 0 | 0 | 0 | 16
Question and Answer | low | 0 | 0 | 0 | 0 | 24
Image Management | low | 0 | 0 | 0 | 0 | 16
Design/Build Phase 1 (Data, Integration, and SaaS Architecture) |  | 184 | 1628 | 370 | 191 | 2373 | 3.25 | 18.2538 | 4.5635 | 2024-06-15 09:00 | 2024-10-30 06:42
Order Flow and Structure
Import File mapping utility | medium | 24 | 60 | 17 | 9 | 110
Import Validation | low | 16 | 60 | 16 | 8 | 100
Import method configuration module | high | 16 | 100 | 24 | 12 | 152
Import schedule configuration module | low | 8 | 36 | 9 | 5 | 58
Order assignment, value, completion methodology | high | 8 | 100 | 22 | 11 | 141
Products and Forms |  |  |  | 0 | 0 | 0
Form Structure Builder Module Framework | high | 12 | 120 | 27 | 14 | 173
PDF output configuration Module Framework | high | 12 | 120 | 27 | 14 | 173
Display and Validation Module Framework | medium | 12 | 100 | 23 | 12 | 147
Product Builder Module Framework | medium | 12 | 100 | 23 | 12 | 147
AR/AP Module Framework | low | 12 | 60 | 15 | 8 | 95
Question and Answer management module Framework | low | 12 | 60 | 15 | 8 | 95
Client Integration Service Layer |  |  |  | 0 | 0 | 0
Supporting API Structure | High |  | 240 | 48 | 24 | 312
Data Management | High |  | 160 | 32 | 16 | 208
Logging and Persistence | medium |  | 80 | 16 | 8 | 104
RCT | low |  | 24 | 5 | 3 | 32
LC360 | low |  | 24 | 5 | 3 | 32
Pioneer | low |  | 24 | 5 | 3 | 32
Hub and Spoke SaaS Architecture |  |  |  | 0 | 0 | 0
Multi-tenant client catalog management | medium | 16 | 40 | 12 | 6 | 74
SSO client user management | medium | 24 | 40 | 13 | 7 | 84
SaaS subscription architecture | medium |  | 80 | 16 | 8 | 104
Design/Build Phase 2 (User Facing) |  | 1140 | 568 | 339 | 173 | 2220 | 3.25 | 17.0769 | 4.2692 | 2024-10-30 06:42 | 2025-03-07 08:32
Client Managed Administration
Question Display, Nesting and Validation Module | medium | 140 | 24 | 33 | 17 | 214
AR/AP Module | low | 32 | 16 | 10 | 5 | 63
Question and Answer management module | low | 32 | 16 | 10 | 5 | 63
Product Builder Module | medium | 40 | 24 | 13 | 7 | 84
Form Builder Module | high | 80 | 36 | 24 | 12 | 152
Output Builder | high | 80 | 36 | 24 | 12 | 152
Order assignment, value, completion methodology | high | 80 | 24 | 21 | 11 | 136
Communication Management and Frameworks |  |  |  | 0 | 0 | 0
SendGrid Automations | medium | 16 | 32 | 10 | 5 | 63
Notification management | medium | 16 | 32 | 10 | 5 | 63
VOIP infrastructure | medium |  |  |  |  | 0
HiMarley | medium | 40 | 40 | 16 | 8 | 104
Third Party integration management | [5 empty] | 0
Valuation Engine mapping Module | medium | 40 | 40 | 16 | 8 | 104
Policy Management | medium | 40 | 20 | 12 | 6 | 78
QuickBooks Integration |  |  | 40 |  |  | 40
Service Management | medium | 40 | 20 | 12 | 6 | 78
Portals |  |  |  | 0 | 0 | 0
System Administration | medium | 80 | 40 | 24 | 12 | 156
Tenant Administration | medium | 24 | 16 | 8 | 4 | 52
Field Rep | medium | 80 | 24 | 21 | 11 | 136
QA | medium | 80 | 24 | 21 | 11 | 136
Client | medium | 80 | 24 | 21 | 11 | 136
Customer User Portal | medium | 80 | 24 | 21 | 11 | 136
Underwriter Portal | medium | 40 | 16 | 12 | 6 | 74
Design/Build Phase 3 (Reporting and Apps) |  | 640 | 460 | 221 | 112 | 1433 | 3.25 | 11.0231 | 2.7558 | 2025-03-07 08:32 | 2025-05-29 00:42
Imbedded Reporting
Domo integration | medium | 40 | 60 | 20 | 10 | 130
Additional Platform Identification | high |  |  | 0 | 0 | 0
Self Inspection App | [5 empty] | 0
Form Builder Module | medium | 32 | 40 | 15 | 8 | 95
Data management Module | medium | 24 | 40 | 13 | 7 | 84
Application flow Module | medium | 24 | 40 | 13 | 7 | 84
Native Mobile App | [5 empty] | 0
Commercial Lines Support V2 | high | 240 | 40 | 56 | 28 | 364
Personal Lines Support V2 | high | 160 | 20 | 36 | 18 | 234
AI Technologies | [5 empty] | 0
AI image processing and detection | high |  | 100 | 20 | 10 | 130
Phase 3 GO-Live |  |  |  | 0 | 0 | 0
Burn-in and Support | high | 120 | 120 | 48 | 24 | 312
Design/Build Phase 4 (SaaS Admin) |  | 180 | 80 | 53 | 28 | 341 | 3.25 | 2.6231 | 0.65577 | 2025-05-29 00:42 | 2025-06-17 16:51
SaaS Portals |  |  |  | 0 | 0 | 0
Multi-tenant client catalog management | medium | 60 | 24 | 17 | 9 | 110
SSO client user management | medium | 60 | 32 | 19 | 10 | 121
SaaS subscription Management | medium | 60 | 24 | 17 | 9 | 110
Design/Build Phase 5 (AI Enhancements) |  | 200 | 200 | 80 | 40 | 520
AI Additions
AI managed output builder | high | 40 | 40 | 16 | 8 | 104
AI managed form builder | high | 40 | 40 | 16 | 8 | 104
Special Instructions Intent Module | high |  | 40 | 8 | 4 | 52
AI Address Validation | high | 40 | 40 | 16 | 8 | 104
Offline AI Photo Check | high | 40 |  | 8 | 4 | 52
AI QA Support | high | 40 |  | 8 | 4 | 52
System Integration | high |  | 40 | 8 | 4 | 52
Project management |  | 0 |  |  |  | 500